## Sheet1
SN | Requirements | Status
1 | Reports
1.1 | Extract report for all of the employee's personal information, directorate, department, title and line manager. | Done
1.2 | Payroll report to be customised based on the manual AFC template | Template to be shared by John
2 | System Fields
2.1 | Bank Details - Restrictions for IBAN numbers 29, Swift code 8 | Done
2.2 | Paid Leave Balance to be 2 days per each completed month | Done
2.3 | Add the name of days in the calendar and highlight the weekends | Done
2.4 | link the start date of the contract to the timesheet calculations | Done
2.5 | Template of invoice to be generated to reflect the final paid amount | Done
2.6 | Bulk upload tab for adding more than one employee information | Raafat/Prakash to upload the initial batch for FIC
2.7 | HR Letters templates (Salary Certificate/Certificate of Appreciation) | Phase 2 - not a current priority
3 | Dashboard
3.1 | Chart for total payroll budget and utlisation per month | To be developed
3.2 | Chart for breakdown of employees per directorate/department/FA | Done
3.3 | Chart for type of entity | Done
3.4 | Chart for Gender | Done
3.5 | Chart for local/international hires | To be developed | ??
3.6 | Chart for nationalities | Done
4 | Invoices
4.1 | Invoices should have the parameter to be calucated based on each month (30 - 31) days | Done
4.2 | Comments in the invoice should be reflective per month | To be developed
4.3 | A Line for - Payment due date to be removed | Done
4.4 | One additional step of approvals to be captured for payroll on all invoices | To be developed
5 | Leaves
5.1 | Leaves tracker report to be generated based on the total leaves granted and how many leaves utlisied | To be developed